## Campaign Overview
Date Added | Campaign | End Date | Deadline | Implementation Team | CSM Team Member | Total Sales | Status | Actual Sales | Campaign Pacing | Progress | Leads Per Day | Leads Should Complete | FALSE
2024-09-01 | Radicle Inc | 2024-09-03 | 2024-09-04 | Laura | Terrence Strickland | 300 | Complete | 250 | 83.33% |  | 150 | 300 | FALSE
2024-09-02 | sendit ¦ lens games | 2024-09-06 | 2024-09-18 | Sevika | Amanda | 450 | Complete | 100 | 22.22% |  | 112.5 | 450 | FALSE
2024-09-03 | Consult Vito | 2024-09-06 | 2024-09-30 | Sevika | Terrence Strickland | 100 | Complete | 100 | 100% |  | 33.3333 | 100 | FALSE
2024-09-04 | Snap Inc. | 2024-09-07 | 2024-09-30 | Laura | Amanda | 200 | Off Pace | 50 | 25% |  | 66.6667 | 200 | FALSE
2024-09-05 | SRG / Emergint | 2024-09-05 | 2024-09-30 | Laura | Amanda | 300 | Slightly Behind | 300 | 100% |  | #DIV/0! | #DIV/0! | FALSE
2024-09-06 | Linked4Biz | 2024-09-06 | 2024-09-30 | Laura | Terrence Strickland | 400 | Off Pace | 88 | 22% |  | #DIV/0! | #DIV/0! | FALSE
2024-09-07 | Scribd | 2024-09-09 | 2024-09-30 | Laura | Terrence Strickland | 500 | Complete | 500 | 100% |  | 250 | 500 | FALSE
2024-09-08 | Famous Wolf ¦ Social Media Agency | 2024-09-09 | 2024-09-30 | Sevika | Terrence Strickland | 600 | Complete | 600 | 100% |  | 600 | 600 | FALSE
2024-09-09 | School of Rock | 2024-09-09 | 2024-09-30 | Sevika | Terrence Strickland | 700 | Complete | 700 | 100% |  | #DIV/0! | #DIV/0! | FALSE
2024-09-10 | Miami Dade College | 2024-09-14 | 2024-09-30 | Sevika | Terrence Strickland | 800 | Slightly Behind | 300 | 37.5% |  | 200 | 800 | FALSE
2024-09-11 | Lead Cookie | 2024-09-14 | 2024-09-30 | Sevika | Terrence Strickland | 900 | Complete | 900 | 100% |  | 300 | 900 | FALSE
2024-09-12 | Movebubble | 2024-09-15 | 2024-09-30 | Sevika | Terrence Strickland | 1000 | Off Pace | 400 | 40% |  | 333.3333 | 1000 | FALSE
2024-09-13 | MLB Advanced Media, L.P. | 2024-09-20 | 2024-09-30 | Sevika | Terrence Strickland | 2000 | Pacing | 1900 | 95% |  | 285.7143 | 1714.2857 | FALSE
2024-09-14 | TW3radio | 2024-09-21 | 2024-09-30 | Laura | Amanda | 3000 | Complete | 3000 | 100% |  | 428.5714 | 2142.8571 | FALSE
2024-09-15 | DoControl | 2024-09-22 | 2024-09-30 | Laura | Amanda | 4000 | Pacing | 2800 | 70% |  | 571.4286 | 2285.7143 | FALSE
2024-09-16 | The Smartworking Company® | 2024-09-23 | 2024-09-30 | Laura | Amanda | 5000 | Pacing | 3456 | 69.12% |  | 714.2857 | 2142.8571 | FALSE
2024-09-17 | Miro | 2024-09-25 | 2024-09-30 | Sevika | Amanda | 6000 | Off Pace | 888 | 14.8% |  | 750 | 1500 | FALSE
2024-09-18 | WebConversion | 2024-09-27 | 2024-09-30 | Laura | Terrence Strickland | 7000 | Pacing | 999 | 14.27% |  | 777.7778 | 777.7778 | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Daily Targets
Date | Campaign Name | CSM Team Members | OPS Team Member | Target | Campaign Name (Target)
2024-09-02 | Radicle Inc | Terrence Strickland | Sevika | 10 | Radicle Inc (10)
2024-09-03 | sendit ¦ lens games | Amanda | Laura | 100 | sendit ¦ lens games (100)

## Daily Delivery Schedule - Calen
Deadine/EndDate |  | Team Member |  | Status |  | Campaign
Deadline |  | All |  | All
2024-09-18
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07
Radicle Inc
2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14
2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21
sendit ¦ lens games
2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28
2024-09-29 | 2024-09-30
Consult Vito
Snap Inc.
SRG / Emergint
Linked4Biz
Scribd

## Daily Targets - Calendar
Team Member
All
2024-09-18
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07
| Radicle Inc (10) | sendit ¦ lens games (100)
2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14
2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21
2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28
2024-09-29 | 2024-09-30

## Actual Deliveries
Delivery Date | Campaign | Unit Volume | Unit Volume - Campaign
2024-09-09 | School of Rock | 300 | 300 - School of Rock
2024-09-11 | Lead Cookie | 440 | 440 - Lead Cookie
2024-09-13 | DoControl | 15 | 15 - DoControl
2024-09-30 | Miro | 35 | 35 - Miro

## Actual Deliveries - Calendar
Campaign
2024-09-18
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07
2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14
| 300 - School of Rock |  | 440 - Lead Cookie |  | 15 - DoControl
2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21
2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28
2024-09-29 | 2024-09-30
35 - Miro

## Settings
OPS Team Members | CSM Team Members | Statuses | Deadline | All | All
Laura | Terrence Strickland | Pacing | End Date | Laura | All Incomplete
Sevika | Amanda | Complete |  | Sevika | Pacing
|  | On Pace |  |  | Complete
|  | Slightly Behind |  |  | On Pace
|  | Off Pace |  |  | Slightly Behind
Off Pace

## Logic
The Date | 2024-09-18 | 1 | Sunday | January | 1
Month Start | 2024-09-01 | 2 | Monday | February | 2
Month End | 2024-09-30 | 3 | Tuesday | March | 3
|  | 4 | Wednesday | April | 4
Next Month | 2024-10-01 | 5 | Thursday | May | 5
Previous Month | 2024-08-01 | 6 | Friday | June | 6
Today | 2024-09-19 | 7 | Saturday | July | 7
|  |  |  | August | 8
|  |  |  | September | 9
|  |  |  | October | 10
|  |  |  | November | 11
|  |  |  | December | 12